## Weekly Status Report
☁ AWS Security Hub — Remediation Status Report
AWS Foundational Security Best Practices (FSBP) v1.0.0 ¦ Region: ca-central-1 ¦ Generated: 2026-03-10 18:07 UTC
Report Date: | 2026-03-10 | Region: | ca-central-1 | Accounts in Scope: | 3 | Go-Live Target: | May 2025
CRITICAL FINDINGS |  | HIGH FINDINGS |  | MEDIUM FINDINGS |  | REMEDIATED
WEEKLY SUMMARY — Complete before sending to CISO
Remediation Progress: |  | 5 findings remediated of 56 total. 27 critical and 9 high severity findings remain open across 3 AWS account(s).
Blockers / Dependencies:
Cloud Engineering Actions Required:
Risks to Go-Live Timeline: |  | ⚠ 27 CRITICAL findings unresolved — must address before go-live.
Planned for Next Week:

## Findings
AWS FSBP v1.0.0 — Security Hub Findings ¦ 56 findings ¦ Pulled: 2026-03-10 18:07 UTC
Control ID | Title | Category | Account ID | Region | Resource ID | Resource Type | Severity | Status | First Seen | Last Updated | Remediation Guide | Assigned To | Date Remediated | Ticket / PR Ref | Notes
IAM.1 | IAM policies should not allow full '*:*' administrative privileges | Identity & Access Management | 123456789012 | ca-central-1 | arn:aws:iam::123456789012:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.1
IAM.1 | IAM policies should not allow full '*:*' administrative privileges | Identity & Access Management | 234567890123 | ca-central-1 | arn:aws:iam::234567890123:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.1
IAM.1 | IAM policies should not allow full '*:*' administrative privileges | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.1
IAM.4 | IAM root user access key should not exist | Identity & Access Management | 123456789012 | ca-central-1 | arn:aws:iam::123456789012:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.4
IAM.4 | IAM root user access key should not exist | Identity & Access Management | 234567890123 | ca-central-1 | arn:aws:iam::234567890123:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.4
IAM.4 | IAM root user access key should not exist | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.4
IAM.6 | Hardware MFA should be enabled for the root user | Identity & Access Management | 123456789012 | ca-central-1 | arn:aws:iam::123456789012:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.6
IAM.6 | Hardware MFA should be enabled for the root user | Identity & Access Management | 234567890123 | ca-central-1 | arn:aws:iam::234567890123:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.6
IAM.6 | Hardware MFA should be enabled for the root user | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.6
IAM.9 | MFA should be enabled for the root user | Identity & Access Management | 123456789012 | ca-central-1 | arn:aws:iam::123456789012:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.9
IAM.9 | MFA should be enabled for the root user | Identity & Access Management | 234567890123 | ca-central-1 | arn:aws:iam::234567890123:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.9
IAM.9 | MFA should be enabled for the root user | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.9
S3.1 | S3 Block Public Access setting should be enabled | Data Protection | 123456789012 | ca-central-1 | arn:aws:s3:::momentum-123456789012-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.1
S3.1 | S3 Block Public Access setting should be enabled | Data Protection | 234567890123 | ca-central-1 | arn:aws:s3:::momentum-234567890123-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.1
S3.1 | S3 Block Public Access setting should be enabled | Data Protection | 345678901234 | ca-central-1 | arn:aws:s3:::momentum-345678901234-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.1
S3.2 | S3 buckets should prohibit public read access | Data Protection | 123456789012 | ca-central-1 | arn:aws:s3:::momentum-123456789012-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.2
S3.2 | S3 buckets should prohibit public read access | Data Protection | 234567890123 | ca-central-1 | arn:aws:s3:::momentum-234567890123-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.2
S3.2 | S3 buckets should prohibit public read access | Data Protection | 345678901234 | ca-central-1 | arn:aws:s3:::momentum-345678901234-data | AWS::S3::Bucket | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.2
EC2.1 | Amazon EBS snapshots should not be publicly restorable | Infrastructure Protection | 123456789012 | ca-central-1 | arn:aws:ec2:ca-central-1:123456789012:instance/i-0abc123def456 | AWS::EC2::Instance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.1
EC2.1 | Amazon EBS snapshots should not be publicly restorable | Infrastructure Protection | 234567890123 | ca-central-1 | arn:aws:ec2:ca-central-1:234567890123:instance/i-0abc123def456 | AWS::EC2::Instance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.1
EC2.1 | Amazon EBS snapshots should not be publicly restorable | Infrastructure Protection | 345678901234 | ca-central-1 | arn:aws:ec2:ca-central-1:345678901234:instance/i-0abc123def456 | AWS::EC2::Instance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.1
RDS.2 | RDS DB instances should prohibit public access | Infrastructure Protection | 123456789012 | ca-central-1 | arn:aws:rds:ca-central-1:123456789012:db:momentum-prod | AWS::RDS::DBInstance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.2
RDS.2 | RDS DB instances should prohibit public access | Infrastructure Protection | 234567890123 | ca-central-1 | arn:aws:rds:ca-central-1:234567890123:db:momentum-prod | AWS::RDS::DBInstance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.2
RDS.2 | RDS DB instances should prohibit public access | Infrastructure Protection | 345678901234 | ca-central-1 | arn:aws:rds:ca-central-1:345678901234:db:momentum-prod | AWS::RDS::DBInstance | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.2
Lambda.1 | Lambda function policies should prohibit public access | Infrastructure Protection | 123456789012 | ca-central-1 | arn:aws:lambda:ca-central-1:123456789012:function:momentum-api | AWS::Lambda::Function | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Lambda.1
Lambda.1 | Lambda function policies should prohibit public access | Infrastructure Protection | 234567890123 | ca-central-1 | arn:aws:lambda:ca-central-1:234567890123:function:momentum-api | AWS::Lambda::Function | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Lambda.1
Lambda.1 | Lambda function policies should prohibit public access | Infrastructure Protection | 345678901234 | ca-central-1 | arn:aws:lambda:ca-central-1:345678901234:function:momentum-api | AWS::Lambda::Function | CRITICAL | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Lambda.1
EC2.2 | VPC default security group should not allow inbound or outbound traffic | Infrastructure Protection | 123456789012 | ca-central-1 | arn:aws:ec2:ca-central-1:123456789012:instance/i-0abc123def456 | AWS::EC2::Instance | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.2
EC2.2 | VPC default security group should not allow inbound or outbound traffic | Infrastructure Protection | 345678901234 | ca-central-1 | arn:aws:ec2:ca-central-1:345678901234:instance/i-0abc123def456 | AWS::EC2::Instance | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.2
EC2.2 | VPC default security group should not allow inbound or outbound traffic | Infrastructure Protection | 234567890123 | ca-central-1 | arn:aws:ec2:ca-central-1:234567890123:instance/i-0abc123def456 | AWS::EC2::Instance | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.2
EC2.19 | Security groups should not allow unrestricted access to ports with high risk | Infrastructure Protection | 123456789012 | ca-central-1 | arn:aws:ec2:ca-central-1:123456789012:instance/i-0abc123def456 | AWS::EC2::Instance | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.19
IAM.3 | IAM users' access keys should be rotated every 90 days or less | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.3
IAM.5 | MFA should be enabled for all IAM users that have a console password | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.5
S3.5 | S3 buckets should require requests to use SSL | Data Protection | 345678901234 | ca-central-1 | arn:aws:s3:::momentum-345678901234-data | AWS::S3::Bucket | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.5
S3.5 | S3 buckets should require requests to use SSL | Data Protection | 123456789012 | ca-central-1 | arn:aws:s3:::momentum-123456789012-data | AWS::S3::Bucket | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.5
S3.5 | S3 buckets should require requests to use SSL | Data Protection | 234567890123 | ca-central-1 | arn:aws:s3:::momentum-234567890123-data | AWS::S3::Bucket | HIGH | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.5
CloudTrail.1 | CloudTrail should be enabled with at least one multi-Region trail | Logging & Monitoring | 123456789012 | ca-central-1 | arn:aws:cloudtrail:ca-central-1:123456789012:trail/momentum-trail | AWS::CloudTrail::Trail | HIGH | Remediated | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for CloudTrail.1
EC2.6 | VPC flow logging should be enabled in all VPCs | Logging & Monitoring | 123456789012 | ca-central-1 | arn:aws:ec2:ca-central-1:123456789012:instance/i-0abc123def456 | AWS::EC2::Instance | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.6
EC2.7 | EBS default encryption should be enabled | Data Protection | 345678901234 | ca-central-1 | arn:aws:ec2:ca-central-1:345678901234:instance/i-0abc123def456 | AWS::EC2::Instance | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for EC2.7
RDS.3 | RDS DB instances should have encryption at rest enabled | Data Protection | 123456789012 | ca-central-1 | arn:aws:rds:ca-central-1:123456789012:db:momentum-prod | AWS::RDS::DBInstance | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.3
RDS.3 | RDS DB instances should have encryption at rest enabled | Data Protection | 345678901234 | ca-central-1 | arn:aws:rds:ca-central-1:345678901234:db:momentum-prod | AWS::RDS::DBInstance | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.3
RDS.3 | RDS DB instances should have encryption at rest enabled | Data Protection | 234567890123 | ca-central-1 | arn:aws:rds:ca-central-1:234567890123:db:momentum-prod | AWS::RDS::DBInstance | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for RDS.3
KMS.4 | AWS KMS key rotation should be enabled | Data Protection | 234567890123 | ca-central-1 | arn:aws:kms:ca-central-1:234567890123:key/mrk-abc123 | AWS::KMS::Function | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for KMS.4
Config.1 | AWS Config should be enabled | Logging & Monitoring | 234567890123 | ca-central-1 | arn:aws:config:ca-central-1:234567890123:config-recorder/default | AWS::Config::Function | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Config.1
Config.1 | AWS Config should be enabled | Logging & Monitoring | 123456789012 | ca-central-1 | arn:aws:config:ca-central-1:123456789012:config-recorder/default | AWS::Config::Function | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Config.1
Config.1 | AWS Config should be enabled | Logging & Monitoring | 345678901234 | ca-central-1 | arn:aws:config:ca-central-1:345678901234:config-recorder/default | AWS::Config::Function | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for Config.1
CloudTrail.2 | CloudTrail should have encryption at rest enabled | Logging & Monitoring | 234567890123 | ca-central-1 | arn:aws:cloudtrail:ca-central-1:234567890123:trail/momentum-trail | AWS::CloudTrail::Trail | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for CloudTrail.2
CloudTrail.2 | CloudTrail should have encryption at rest enabled | Logging & Monitoring | 345678901234 | ca-central-1 | arn:aws:cloudtrail:ca-central-1:345678901234:trail/momentum-trail | AWS::CloudTrail::Trail | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for CloudTrail.2
CloudTrail.2 | CloudTrail should have encryption at rest enabled | Logging & Monitoring | 123456789012 | ca-central-1 | arn:aws:cloudtrail:ca-central-1:123456789012:trail/momentum-trail | AWS::CloudTrail::Trail | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for CloudTrail.2
S3.4 | S3 buckets should have server-side encryption enabled | Data Protection | 123456789012 | ca-central-1 | arn:aws:s3:::momentum-123456789012-data | AWS::S3::Bucket | MEDIUM | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for S3.4
GuardDuty.1 | GuardDuty should be enabled | Detection | 123456789012 | ca-central-1 | arn:aws:guardduty:ca-central-1:123456789012:detector/abc123 | AWS::GuardDuty::Function | HIGH | Remediated | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for GuardDuty.1
GuardDuty.1 | GuardDuty should be enabled | Detection | 345678901234 | ca-central-1 | arn:aws:guardduty:ca-central-1:345678901234:detector/abc123 | AWS::GuardDuty::Function | HIGH | Remediated | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for GuardDuty.1
SecurityHub.1 | Security Hub should be enabled | Detection | 123456789012 | ca-central-1 | arn:aws:securityhub:ca-central-1:123456789012:hub/default | AWS::SecurityHub::Function | MEDIUM | Remediated | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for SecurityHub.1
SecurityHub.1 | Security Hub should be enabled | Detection | 234567890123 | ca-central-1 | arn:aws:securityhub:ca-central-1:234567890123:hub/default | AWS::SecurityHub::Function | MEDIUM | Remediated | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for SecurityHub.1
IAM.2 | IAM users should not have IAM policies attached | Identity & Access Management | 345678901234 | ca-central-1 | arn:aws:iam::345678901234:policy/AdminPolicy | AWS::IAM::Policy | LOW | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.2
IAM.2 | IAM users should not have IAM policies attached | Identity & Access Management | 234567890123 | ca-central-1 | arn:aws:iam::234567890123:policy/AdminPolicy | AWS::IAM::Policy | LOW | Open | 2025-01-15 | 2025-03-08 | See AWS Security Hub documentation for IAM.2

## By Severity
Findings Summary by Severity
Severity | Total | Open | In Progress | Remediated | % Remediated
CRITICAL | 27 | 27 | 0 | 0 | 0%
HIGH | 12 | 9 | 0 | 3 | 25%
MEDIUM | 15 | 13 | 0 | 2 | 13%
LOW | 2 | 2 | 0 | 0 | 0%
INFORMATIONAL | 0 | 0 | 0 | 0 | 0%
TOTAL | 56 | 51 | 0 | 5 | 9%

## By Account
Findings by AWS Account
Account ID | Total | Critical | High | Medium | Remediated | % Remediated
123456789012 | 20 | 9 | 5 | 6 | 3 | 15%
234567890123 | 17 | 9 | 2 | 5 | 1 | 6%
345678901234 | 19 | 9 | 5 | 4 | 1 | 5%

## By Control
Top Failing Controls — FSBP v1.0.0
Control ID | Title | Severity | Failing Resources | Accounts Affected | Remediation URL
IAM.1 | IAM policies should not allow full '*:*' administrative privileges | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
IAM.4 | IAM root user access key should not exist | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
IAM.6 | Hardware MFA should be enabled for the root user | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
IAM.9 | MFA should be enabled for the root user | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
S3.1 | S3 Block Public Access setting should be enabled | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/s3-controls.html
S3.2 | S3 buckets should prohibit public read access | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/s3-controls.html
EC2.1 | Amazon EBS snapshots should not be publicly restorable | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html
RDS.2 | RDS DB instances should prohibit public access | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/rds-controls.html
Lambda.1 | Lambda function policies should prohibit public access | CRITICAL | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/lambda-controls.html
EC2.2 | VPC default security group should not allow inbound or outbound traffic | HIGH | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html
S3.5 | S3 buckets should require requests to use SSL | HIGH | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/s3-controls.html
EC2.19 | Security groups should not allow unrestricted access to ports with high risk | HIGH | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html
IAM.3 | IAM users' access keys should be rotated every 90 days or less | HIGH | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
IAM.5 | MFA should be enabled for all IAM users that have a console password | HIGH | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html
RDS.3 | RDS DB instances should have encryption at rest enabled | MEDIUM | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/rds-controls.html
Config.1 | AWS Config should be enabled | MEDIUM | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/config-controls.html
CloudTrail.2 | CloudTrail should have encryption at rest enabled | MEDIUM | 3 | 3 | https://docs.aws.amazon.com/securityhub/latest/userguide/cloudtrail-controls.html
EC2.6 | VPC flow logging should be enabled in all VPCs | MEDIUM | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html
EC2.7 | EBS default encryption should be enabled | MEDIUM | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/ec2-controls.html
KMS.4 | AWS KMS key rotation should be enabled | MEDIUM | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/kms-controls.html
S3.4 | S3 buckets should have server-side encryption enabled | MEDIUM | 1 | 1 | https://docs.aws.amazon.com/securityhub/latest/userguide/s3-controls.html
IAM.2 | IAM users should not have IAM policies attached | LOW | 2 | 2 | https://docs.aws.amazon.com/securityhub/latest/userguide/iam-controls.html